## RTM
ID: 1
Users should be able to open a new User account with the Planetarium
Passwords should never be visible in plaintext
Users should have unique usernames
Usernames and passwords should not be longer than 30 characters
given the user is on the login page
when the user clicks the create account button
when the user provides a valid name and password and clicks the create button
then the user should be given an alert saying their account has been created successfully
and the user should be redirected to the login page
given the user is on the login page
when the user clicks the create account button
when the user provides an invalid name and/or password and clicks the create button
then the user should be given an alert saying their account hasnot been created successfully
and the user should stay on the registration page

## Strategy
ID: 1
Boundary Analysis testing for username/password length
Equivalence Partition testing for the uniqueness of usernames
Exploratory Testing to see if passwords are in plain text in any places we have access to in the provided software
Error Guess Testing to see if the passwords are in plain text in the interface for the application a regular user would have access to
Error Guess Testing to perform Acceptance Testing for the Use Case

## Schedule
Phase | Completion Target | Actual Completion | Key
1. Requirement Analysis | October 17th |  | target met
2. Test Planning | October 21st |  | target missed
3. Test Case Development | October 24th |  | target in progress
4. Test Environment Setup | October 25th
5. Test Execution | October 30th
6. Test Cycle Closure | October 31st

## SRS
System Requirement Specifications in Foundations Project Document